## Report
OSINT
Earned Value Analysis Report
| Prepared By: | [Presley George]
| Date: | 2023-04-28
[42]
| For Period: | 4/11/23 - 5/4/23
Summary:
This is the Planned ValueSpreadsheet used to account for the cost of time spent on each task daily
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | wk 1 | wk 2 | wk 3 | wk 4 | wk 5
1.1 | Create a concept | 1000 | 1000 | 0 | 0 | 0 | 0
1.2 | Develop Process for Intel Collection | 1400 | 200 | 400 | 400 | 400 | 0
1.3 | Create Dashboard | 1440 | 0 | 360 | 360 | 360 | 360
1.4 | Create software program | 1200 | 0 | 300 | 300 | 300 | 300
1.5 | Generate report for analysis | 1600 | 0 | 0 | 400 | 400 | 800
1.6 | Present Report for analysis | 1000 | 0 | 0 | 0 | 0 | 1000
1.7 | Project management | 2000 | 200 | 400 | 400 | 400 | 600
0
0
0
0
0
Insert new rows above this one
| Total Budgeted Cost | 9640 | 1400 | 1460 | 1860 | 1860 | 3060
|  | Cumulative Planned Value (PV) | 1400 | 2860 | 4720 | 6580 | 9640
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 1400 | 3060 | 5120 | 7180 | 10540
|  | Cumulative Earned Value (EV) | 1270 | 1590 | 3230 | 5040 | 7240
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -130 | -1470 | -1890 | -2140 | -3300
|  | Schedule Variance (SV = EV - PV) | -130 | -1270 | -1490 | -1540 | -2400
|  | Cost Performance Index (CPI = EV/AC) | 0.90714 | 0.51961 | 0.63086 | 0.70195 | 0.68691
|  | Schedule Performance Index (SPI = EV/PV) | 0.90714 | 0.55594 | 0.68432 | 0.76596 | 0.75104
|  | Estimated Cost at Completion (EAC) | 10626.7717 | 18552.4528 | 15280.743 | 13733.1746 | 14033.9227

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP). | [14 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [14 empty] | © 2012 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Create a concept | 1000 | 100%
1.2 | Develop Process for Intel Collection | 1400 | 5% | 35% | 65% | 100%
1.3 | Create Dashboard | 1440 |  | 25% | 50% | 75% | 100%
1.4 | Create software program | 1200 |  | 20% | 40% | 60% | 100%
1.5 | Generate report for analysis | 1600 |  |  | 20% | 40% | 100%
1.6 | Present Report for analysis | 1000 |  |  |  |  | 100%
1.7 | Project management | 2000 | 10% | 25% | 40% | 60% | 100%
- | - | 0
- | - | 0
- | - | 0
- | - | 0
- | - | 0
Insert new rows above this one
|  | Cumulative EV | 1270 | 1590 | 3230 | 5040 | 7240 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1.1 | Create a concept |  | Wk 1: 1000
1.2 | Develop Process for Intel Collection |  | Wk 1: 200; Wk 2: 400; Wk 3: 400; Wk 4: 400
1.3 | Create Dashboard |  | Wk 2: 360; Wk 3: 360; Wk 4: 360; Wk 5: 360
1.4 | Create software program |  | Wk 2: 300; Wk 3: 300; Wk 4: 300; Wk 5: 600
1.5 | Generate report for analysis |  | Wk 3: 400; Wk 4: 400; Wk 5: 800
1.6 | Present Report for analysis |  | Wk 5: 1000
1.7 | Project management |  | Wk 1: 200; Wk 2: 600; Wk 3: 600; Wk 4: 600; Wk 5: 600
- | -
- | -
- | -
- | -
- | -
Insert new rows above this one
|  | Total Actual Cost | 1400 | 1660 | 2060 | 2060 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cumulative Actual Cost (AC) | 1400 | 3060 | 5120 | 7180 | 10540 | 10540 | 10540 | 10540 | 10540 | 10540 | 10540 | 10540