## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | OSINT |  |  |  |  | Project Name: | OSINT
National Center: |  |  | IIT |  |  |  |  | National Center: | IIT
Project Manager Name: |  |  | Vikram, Yash |  |  |  |  | Project Manager Name: | vikram, Yash
Project Description: |  |  | This Project retrieves information from various API sources |  |  |  |  | Project Description: | This Project retrieves information from various API sources
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
| Open | Medium | Medium | Yellow | Communication between groups is not at an ideal level | If group members are not able to communicate effectively than the project will lack a cohesive feel | Organizational/Change Management | Deadlines may be met early or late without complete team knowledge causing a disconnect between groups on the project | If any member is unaware of the teams progress in the project | Avoidance | All information will be available to all group members so that they will be able to keep up to date on project progress | All information will be available to all group members so that they will be able to keep up to date on project progress
| Closed | High | Medium | Closed | Unable to obtain twitter API | If our team cannot obtain the twitter API we will not be able to proceed along with the project as development can be completed | Technology | Deadline of development completion will approach without having obtained the twitter API | If one week before development deadline approaches and twitter API is still not obtained implement contingency plan | Mitigation | Another source to scrape will have to be obtained | A meeting with the professor or TA will be held to discuss what other sources may be good choices to scrape for data on
| Closed | High | Low | Closed | Unable to define what information we are collecting and how we will be collecting it | Analyst team will be unable to define what is going to be analyzed and project will come to a standstill | Strategic | Schedule approaches the required start date with no identified topic for analysis | One week before development start approaches and no information to be collected it defined implement contingency plan | Contingency | A team meeting will be scheduled to discuss our problem | Full team will meet and finalize what information is being sought and what we will be analyzing for
| Open | Medium | Medium | Yellow | Team members will have outside responsibilities that will take them away from the project | If team members have outside obligations then project can fall behind on schedule | Schedule | Members are unable to meet with their group or deadlines are not met | Team member displays an outside responsibility that may affect the project or is unavailable to their team | Transfer | Group members will swap responsibilities so project maintains its schedule | Group members may be changed so their schedule better fits work deadlines
| Closed | Medium | Low | Closed | Development will take longer than previously thought through either problems faced or outside responsibilities | All other deadlines will be pushed back as other teams need project to be coded and working to start their work | Technology | Deadline of development completion will approach without working code | Days prior to the scheduled deadline date with no working code implement contingency plan | Transfer | More team members will be brought onto the development team to provide insights | All members with coding experience will meet with coding team and help them
| Closed | Low | Medium | Closed | Understanding of analysis tools is not full where analysis team does not have a full enough understanding | If skills required to complete the task are not obtained project goals will not be able to be fully reached | Project Resources | Schedule approaching the start date of analysis without a complete skill set in the analysis tools | Days prior to the scheduled start date and no team member is proficient with analysis tools implement contingency plan | Mitigation | Team members will watch tutorials about analysis tools | Team will use youtube to find and watch tutorials on analysis tools
| Open | Medium | Low | Green | Computer failure occurs with a group member leaving them without a workspace | Group member will be delayed in completing any assigned tasks for an indefinite amount of times | Reliability of Systems | Member may be slow in completing work as they will have to find another workspace that they may possibly have to share | Member express to the group that they have a had a technological failure | Transfer | Team member responsibility will have to be transferred to another member or multiple members | Team member will transfer responsibility and try and work as well as possible with another member to complete their tasks
| Closed | Medium | Medium | Closed | Team member lacks the required technology to access all aspects of the project | A team member will not be able to contribute fully to the project | Technology | Team member will have trouble accessing materials and be left out of the loop on project | Member is not able to complete task as they lack the required technology to access materials | Mitigation | Some of the team members responsibility will have to be transferred to another member or multiple members | Team member will transfer responsibility and try and work as well as possible with another member to complete their tasks

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources